# Partnership Agreement

Project No: 2019-2-HU01-KA105-061329

Project Title: Peer Advocacy for Gender Equality

Project period: 01 August 2019 – 31 October 2020 (15 months)

Advance Planning Visit – Budapest, Hungary: 13-14 September 2019 (2 workdays)

Youth Exchange 1 – Budapest, Hungary: 24-29 November 2019 (6 workdays)

Youth Exchange 2 – Seville, Spain: 19-24 April 2020 (6 workdays)

I. Preliminaries:

The following Partnership Agreement should be signed between the Applicant and the Partner organization involved in the above mentioned Erasmus+ Youth Exchange project.

II. Names and Contacts:

a/ Applicant organization (beneficiary of the grant)

Name: Közgazdasági Politechnikum Alternatív Gimnázium

Address: 1096 Budapest, Vendel u. 3., Hungary

Legal Representative: Alojzia Diósi, principal

Contact person: Anna Surányi, sanna@poli.hu

b/ Partner Organization

Name: 11th Geniko Lykio Irakliou

Address: Papa Petrou Gavala 64, 71409 Heraklion, Greece

Legal Representative: Evangelos Sifakis, principal

Contact person: Tom Ioannidis, tioamido@yahoo.gr

III. Roles and Responsibilities of the Applicant and Partner organizations:

The Applicant organization shall

- organize the Advance Planning Visit in Budapest, Hungary on 13-14 September 2019 in order to prepare 1 group leader from each partner for the project activities (book flights, provide accommodation, meals, public transport),

- prepare parental consent to rules & statements to be signed by parents before youth exchanges,

- provide Youthpass for all young participants,

- prepare visibility materials and channels of communication and dissemination on social media and ensure the promotion and dissemination of the project results,

- concerning Youth Exchange 1 in Budapest, Hungary on 24-29 November 2019:

- prepare an infopack about the exchange with the program and all the necessary information,

- book flight tickets for partners – 2 group leaders and 6 youth per each partner,

- arrange accommodation for 6 nights, food and meals, public transport, infrastructure and equipment and ensure the protection and safety of all participants,

- organize all the activities – gender related workshops, presentations, sport activities, energizers, intercultural evenings, etc.,

- select 2 Hungarian group leaders and 6 youth; the latter should be between 14 and 16 with good English skills, taking care of gender balance and giving advantage to those with fewer opportunities (educational difficulties, economic obstacles or health problems),

- prepare Hungarian participants for hosting the exchange - linguistic, intercultural, task related preparation, plus introducing their country/city/organization, intercultural night and energizers,

- concerning Youth Exchange 2 in Seville, Spain on 19-24 April 2020:

- book flight tickets for partners – 2 group leaders and 7 youth per each partner,

- select & prepare 2 Hungarian group leaders and 7 youth (see selection & preparation criteria before),

- have a meeting with parents to inform them about the exchange in Spain and to get the parental consent signed,

- arrange travel from Budapest to Seville, Spain and home, make travel and health insurance for each participant and check if they have a valid European Health Insurance Card.

The Partner organization shall

- send 1 group leader to attend the Advance Planning Visit in Budapest, Hungary on 13-14 September 2019 and prepare for the project activities,

- concerning Youth Exchange 1 in Budapest, Hungary on 24-29 November 2019:

- select 2 group leaders and 6 youth; the latter should be between 14 and 16 with good English skills, taking care of gender balance and giving advantage to those with fewer opportunities (educational difficulties, economic obstacles or health problems),

- prepare young participants for the exchange - linguistic, intercultural, task related preparation, plus introducing their country/city/organization, intercultural night and energizers,

- have a meeting with parents to inform them about the exchange in Hungary and to get the parental consent signed,

- make travel and health insurance for each participant and check if they have a valid European Health Insurance Card,

- concerning Youth Exchange 2 in Seville, Spain on 19-24 April 2020:

- select & prepare 2 group leaders and 7 youth (see selection & preparation criteria before),

- have a meeting with parents to inform them about the exchange in Hungary and to get the parental consent signed,

- make travel and health insurance for each participant and check if they have a valid European Health Insurance Card,

- help the Applicant organization with

- facilitating their young participants to carry out home assignments after both youth exchanges – field research, social and online media campaign among their mates;

- the visibility and dissemination of the project results after both youth exchanges with posting blogs, photos and videos on the project Facebook page and their school websites,

- information needed for the final report.

IV. Financial Conditions:

The Applicant organization shall cover all relating costs from the project budget, except travel and health insurance of participants.

The Applicant organization is also responsible for booking flight tickets to Budapest, Hungary for the APV (1 group leader) and Youth Exchange 1 (8 persons) to the maximum of 275 EUR/participant, while for Youth Exchange 2 (9 persons) to the maximum of 360 EUR/participant. The Partner organization shall provide all tickets and boarding passes to the Applicant organization.

V. Signatures

By signing this Partnership Agreement, the partners agree on jointly carrying out the project in the frame of the conditions set out above, and agree to comply with the guidelines of the Erasmus+ Youth In Action programme.

The partners allow the European Commission and the involved National Agencies to use all the data provided in the frame of this project for the purposes of managing the Erasmus+ Youth In Action programme. All data, on paper or electronically, will always be used respecting the privacy of individual persons.

| Applicant Organization Közgazdasági Politechnikum Alternatív Gimnázium | Partner Organization 11th Geniko Lykio Irakliou |
| --- | --- |
| Name of legal representative: Alojzia Diósi Position/function: principal | Name of legal representative: Evangelos Sifakis Position/function: principal |
| Signature and stamp: | Signature and stamp: |
| Place: Budapest, Hungary Date: ......./....../2019 | Place: Date: ......./....../2019 |